## 2019
Task | Start Date | Duration (Days)
1. Program logic model | 2019-02-04 | 15 | Change the start dates as needed. After entering new start dates, the bars in the bar graph may disappear.
2. Dimensions/importance weighting | 2019-02-11 | 15 | Then, use this function =DATEVALUE("mm/dd/yyyy") to find out about the start and end date values.
3. Data collection methods | 2019-02-18 | 10 | And, go to 'Format Axis' setting of the bar graph and replace minimum/maximum bound values with new values.
4. Evaluation proposal writing/approval | 2019-02-25 | 7 | For example, if 9/04/2019 is the new start date, =DATEVALUE("9/04/2019") will show 43712. | 43712
5. Data collection instruments | 2019-03-04 | 20 | And, that's the number you want to use as the minimum bound value.
6. Data collection | 2019-03-18 | 20
7. Data anlaysis with rubrics | 2019-04-01 | 20
8. Conclusions | 2019-04-15 | 10
9. Evaluation final report writing/submission | 2019-04-22 | 15