## Slide 1
Managing Events: Real Challenges, Real Outcomes, 2e
© Liz Quick

## Slide 2: Chapter 2 The delivery phase

## Slide 3: Learning objectives
To help identify and understand:
  On-site management
  Event documents
  Stakeholder liaison
  Pre checks and rehearsals
  Health and safety checks and emergency procedures

## Slide 4: On-site management
Careful planning in the pre-event planning stage will help ensure the on-site delivery runs smoothly
Invariably, there are elements that do not go according to plan
The more prepared the event team are pre-event, the better equipped they are to deal with any eventualities that occur on-site.

## Slide 5: Areas to consider
Event registration
Staff scheduling
Managing staff safety
Event catering
Serving of alcohol on site
Developing an on-site programme schedule
Making changes to the programme
Cancellation of the event
Managing budgetary changes at the event

## Slide 6: Event delivery checks (1 of 2)
Consult with all parties directly involved in the programme
Calculate the time of each activity
Ensure that the programme has time for ‘ceremonial’ activities, that is, opening and/or closing ceremonies, speeches, entertainment or the presentation of awards
Confirm that the venue is available for the whole duration of the event

## Slide 7: Event delivery checks (2 of 2)
Choose an event date that does not clash with other major events in the same location of topic area
Allow for a little ‘slack’ time between activities
Plan the structure of the event and order of activities
Decide how the printed programme will be published

## Slide 8: Event documents
The conference working document
The production schedule
The venue report
The on-site report form
Event contracts and terms and conditions
Risk management documentation
Copies of any relevant licenses
Air and transportation reports / Flight manifest details

## Slide 9: Stakeholder liaison
Conducting staff briefings
Issuing duty rosters
Monitoring of staff performance
Managing other vendors, suppliers and support services
On-site client liaison
Handling Press & Public Relations (PR) requirements at the event
Managing press and VIP guests
Managing sponsors on site
On-site venue liaison

## Slide 10: Managing the client on site
Establish event goals, objectives and ground rules and communicate these to the client
Regularly update the client on any changes on site especially financial ones
Hold regular briefing meetings on-site and record these where necessary
Document everything
Check the client is happy with their room/facilities, etc.
Try to build trust and confidence with the client and own your expertise

## Slide 11: Managing catering checks on site
Special dietary requirements and who has requested these
The menu and meal content and any guest allergies, or other special needs
The use of coloured dots on delegate badges, to indicate special dietary requirements
Serving food and canapés out of different exits to disperse evenly
Exact buffet layouts and positioning to minimise queuing.
The timings for serving any hot and cold food

## Slide 12: Items for staff briefings
Event background, client details and reporting structures
Who does what and when on-site
The site access and build
Facilities and lay out
Arrivals on site, especially flight arrivals and transportation
Recap of conference and /or social programme
Communication of vital information, that is, delegate profile, budgetary signatories, timings to all those working on site
Briefing documents and health and safety and emergency procedures

## Slide 13: Press & public relations (PR) requirements
Media relations
Community relations
Public affairs and government relations
Events as promotional tools for companies
Employee relations (parties, picnics, incentive travel, charity fundraisers, rewards, etc.)
Investor/Donor Relations (annual reports/meetings, CSR, pension programs, etc.)

## Slide 14: Pre-checks and rehearsals
The on-site set-up phase can be the busiest time for the operation and production crew
Often many changes need to be executed to the programme
Regardless of the event type and size, basic tasks need to be completed before delegates or attendees arrive
A few simple procedures and checks can help ensure all runs smoothly on-site

## Slide 15: Venue checks
Acquire any license or permits necessary
Brief event and venue staff on communication processes
Implement contingency plans for routine as well as emergency situations
Meet with the venue staff or conference and events manager beforehand
Run through the event proceedings, room allocations, layouts and catering provision
Liaise with the venue to ensure there is sufficient signage, a registration area, a cloakroom and a welcome desk
Set up the registration desk with any badges, conference packs, stalls, attractions, etc.
Check there are sufficient seats for all attendees

## Slide 16: Additional checks
Meeting rooms are correctly set up with a screen, microphones, a top table, lectern, the correct audio-visual equipment
Make sure the meeting rooms are supplied with paper, pens, water, etc.
The availability of replacement or back-up equipment
Any additional off-site restaurants or venues that will be used
Cleanliness of facilities, private and public areas, inside and outside areas and restrooms
Whether any room-drops of delegate gifts or conference packs to be delivered or guest announcements

## Slide 17: Rehearsals
Technical rehearsals for all the crew and guest speakers are needed at events with significant production requirements
Any last-minute adjustments should be made to presentation material
The production crew should arrange a brief technical rehearsal beforehand for all speakers or entertainment acts
Timing checks are important to make sure speakers do not overrun

## Slide 18: Managing press on-site
Check the location of electrical outlets
Set up a table to seat any spokespeople
Provide seating for reporters and their equipment
Display any visuals as a backdrop to the table
Have a sign-in pad for attendance
Provide a podium for the moderator/speakers
Set up a refreshment desk or area

## Slide 19: Health and safety checks and emergency procedures
Identify emergency routes
Identification of holding areas
Crowd and transportation management
Food and beverage safety
The provision of an emergency plan and first aid facilities
Accident reporting procedures put in place

## Slide 20: Risk assessment
Identify the hazards
Assess these: high, medium or low
Act to reduce these with methods and measures to reduce the risk
Re-assess the risks after action has been taken
Monitor the risks and re-assess
Consult the experts if necessary
Record and report any actions

## Slide 21: Chapter summary questions
Why is it preferential to bring online documentation, rather than paper-based on-site?
What means can be employed to make the registration process easier at events?
What licenses are needed to work with animals on site and which organisation in the UK usually monitors this?
Why is it important to ask guests whether they have any allergies, before serving them food?
Why is it important to conduct on-site staff briefings before the event commences?
What form would you ask a client to sign if they commissioned changes to the programme on-site that would impact the budget?

## Slide 22: Activities
Put together a duty roster for a launch of a new Beaujolais nouveau wine for 50 guests that will run in a local restaurant from 19.00–22.00 hours
Write an email to a local newspaper inviting them to attend the wine launch. How would you incentivise them to attend?
Compile an agenda of key items to cover at a health and safety briefing of volunteers before the wine launch