## Slide 1
Managing Events: Real Challenges, Real Outcomes, 2e
© Liz Quick

## Slide 2: Chapter 1 The planning phase

## Slide 3: Learning objectives
To help identify and understand:
  The event cycle
  The planning process
  Managing stakeholders
  The structure of the industry
  The changing face of events

## Slide 4: The event cycle (1 of 2)
The planning phase
The delivery phase
The evaluation phase

## Slide 5: The event cycle (2 of 2)

## Slide 6: The planning phase
The most important phase of the event cycle
Invariably it will determine its success
The first task is to establish a formal strategic plan
The plan should identify the vision and detail and:
  Establish the vision
  Develop the event objectives
  Implement operational plans
  Devise control systems
  Shutdown and evaluation

## Slide 7: The planning process
Define the objectives
Set the budget
Choose the venue
Invite the audience
Design the programme content
Select catering, entertainment and audio-visual provision
Choose the team
Liaise with stakeholders and suppliers
Determine how to evaluate

## Slide 8: The lead-in period
What happens during the lead-in period | The impact of a short lead-in period
Planning Booking entertainment Venue sourcing- Sourcing suppliers Client liaison Liaison with suppliers, such as caterers Research schedule, that is, producing documents, that is, production schedule Fact-finding | Limits creativity – as no time Unavailability of suppliers and venues Limits choice Compromises decisions Costs more Reactive, rather than proactive management

## Slide 9: Reasons to have a ‘real-time’ meeting
To increase company retention
To foster renewed loyalty
To impart information
To educate or deliver an educative lecture to the audience
To introduce a new culture or management structure
To allow delegates to network and interact
To launch a new product
To enhance sales potential and company motivation
To entertain and have fun

## Slide 10: Managing stakeholders (1 of 2)
Successful events need to meet the expectations of the many stakeholders involved
A ‘stakeholder’ is anyone who has an interest in the value that the organisation creates
Events stakeholders can have varying needs – one stakeholder’s gain may be another’s loss
Stakeholders’ expectations for and attitudes towards the event have a considerable impact on the overall experience and success of it

## Slide 11: Managing stakeholders (2 of 2)
Owners
Customers or Consumers
Sponsors
Employees/volunteers
The event community

## Slide 12: The structure of the industry

## Slide 13: Event buyers
The company or organisation holding the budget and purchasing event services
  Corporate companies, agencies, associations
  Private or public sector
  Individual or entrepreneurial buyer
Entrepreneurs make their money by seeing a new opportunity and starting a venture

## Slide 14: Agencies and intermediaries (1 of 2)
The agency or intermediary is the ‘middleman’ between buyer and supplier.
They have both expertise and buying power and can negotiate optimum rates

## Slide 15: Agencies and intermediaries (2 of 2)
Event management agency/company
Venue search agency
Production company
Destination management company (DMC)
Corporate events company
Representation company
Business travel agency

## Slide 16: Suppliers
Suppliers provide many products and services within the event industry
A few of main suppliers to the industry are as follows:
-Venues
-Destinations
-Airline and transportation companies
-Other suppliers to the events industry i.e. Floral and marquee companies

## Slide 17: The changing face of events
Events have their origins in ancient history, in the form of organised acts and performances
We celebrate milestone events throughout our lives often known as ‘rites of passage’
These events vary according to our cultural background and beliefs
In modern times, events also make a key contribution to social and economic development
Events impact tourism within a destination and can leave a lasting legacy

## Slide 18: The event sector

## Slide 19: Event typologies
The following typologies are often used to classify events:
  Mega-events
  Special events
  Sporting events
  Hallmark events
  Major events
  Cultural events and Festivals
  Minor and small-scale events

## Slide 20: Mega events
Olympic Games
Paralympics Games
Commonwealth Games
FIFA World Cup (Fédération Internationale de Football Association)
World Fairs and Expositions
European Capital of Culture
IAAF World Championships (International Association of Athletics Federations)

## Slide 21: Special events
National days and celebrations
Important civic occasions
Unique cultural performances
Major sporting fixtures
Corporate functions
Trade promotions
Product launches

## Slide 22: Hallmark events
Tour de France
Carnival in Rio
Oktoberfest, Munich
Edinburgh International Festival
Mardi Gras, New Orleans
Pride, Brighton or Sydney

## Slide 23: Chapter summary questions
Why is it important to treat volunteers well, especially on site?
What are the advantages of outsourcing to an agency or intermediary?
Who is usually responsible for promoting and marketing a host destination?
What are rites of passage or milestone events and provide examples?
What are hallmark events usually synonymous with?
How can the word ‘culture’ be linked to events?

## Slide 24: Activities
Develop an aim and 3 objectives for holding the following events:
  CarFest, UK
  Paris Fashion Week
  COP 31, Australia
Find an event taking place in a venue in any country that could be moved and identify an alternative venue for that event, in a different country.
Research three potential sponsors that might have an interest in providing funding and sponsorship for an event called ‘Female Empowerment in Sport’